## Slide 1
Seatrium SAP Pegasus (OEP)
Archival & Migration to Seatrium Cloud
Internal Team Briefing | NTT DATA
March 2026 | Confidential
NTT DATA

## Slide 2
Current SAP Landscape at Seatrium
NTT DATA | Confidential | Seatrium SAP Pegasus Migration
SAP RISE Environment
• Pegasus (OEP) – Since 2021, contract ends Oct 2026
• Optimus (SEP) – Since 2021, migrated to S/4HANA 2025
• High Availability setup with multiple servers
• SAP App + S/4HANA DB + GRC (Access Control Mgmt)
OpenText Archive Center
• Shared by both OEP & SEP systems
• Current size: 18TB → target 16TB by Aug 2026
• Linked to SAP for document archival
• Retention: Audit 5–7 years, SOT 10 years
Seatrium Cloud (Target)
• Local cloud infrastructure managed by Seatrium
• Will host the migrated Pegasus (OEP) system
• Users access via Seatrium WAN
• Display access only – no transactional use
Key Dates
• SAP RISE contract: 2018 – Oct 2026
• Pegasus migration deadline: 30 Oct 2026
• Archive reduction target: 30 Aug 2026
• Current engagement started: 8 Aug 2024

## Slide 3
What Is the Customer Asking For?
NTT DATA | Confidential | Seatrium SAP Pegasus Migration
1. Copy Pegasus Data
All OEP data and attachments to be copied from SAP RISE to Seatrium Cloud
2. New SAP Server Setup
New server in Seatrium Cloud with latest Windows version & service pack hosting SAP Application, S/4HANA Database, and GRC module
3. Display-Only Access
Users access via Seatrium WAN with display access only – no transactional processing
4. GRC Access Control
GRC module to enable users to raise requests for display access
5. Auto User Termination
Automatic termination of SAP user IDs based on Active Directory & Workday using existing batch job processing
6. Archival Best Practices
NTT DATA to propose best practice approach for data archival
7. OpenText Cleanup Support
Support OpenText consultants in deleting SEP and OEP attachments in both Seatrium Cloud and SAP RISE

## Slide 4
Migration Approach – Option 1 (Proposed)
NTT DATA | Confidential | Seatrium SAP Pegasus Migration
FROM: SAP RISE
• Pegasus (OEP) system – multiple HA servers
• SAP Application Server
• S/4HANA Database
• GRC (Access Control Management)
• OpenText Archive Center (shared OEP/SEP)
• Contract period: 2018 – Oct 2026
TO: Seatrium Cloud
• Single server setup (App + DB + GRC)
• Latest Windows version & service pack
• Local copy of OEP attachments
• Display-only access via Seatrium WAN
• Auto user ID termination (AD + Workday)
• Cutover target: 30 Oct 2026
Archive Center Handling
• Archive Center is shared between OEP (Pegasus) and SEP (Optimus) – careful separation needed
• Data reduction from 18TB to 16TB targeted by 30 Aug 2026
• NTT DATA to support OpenText consultants in deletion of SEP and OEP attachments
• Retention policies: Audit records 5–7 years, SOT records 10 years

## Slide 5
Key Considerations & Risks
NTT DATA | Confidential | Seatrium SAP Pegasus Migration
Technical Considerations
• SAP RISE → on-prem migration (non-standard path)
• S/4HANA DB export/import or system copy approach
• GRC module configuration & role migration
• OpenText Archive Center data separation (OEP vs SEP)
• Network connectivity: Seatrium WAN for user access
Data & Compliance
• 18TB archive → 16TB reduction before migration
• Audit retention: 5–7 years required
• SOT retention: 10 years required
• Display-only access – no data modification post-migration
• User ID lifecycle tied to AD & Workday
Timeline Risks
• SAP RISE contract ends Oct 2026 – hard deadline
• Archive reduction must complete by Aug 2026
• OpenText consultant coordination dependency
• Server provisioning & OS patching lead times
Scope Clarity Needed
• Single server vs HA – reduced from multi-server in RISE
• Exact scope of GRC module functionality to retain
• OpenText integration architecture in Seatrium Cloud
• Batch job migration for user ID auto-termination

## Slide 6
NTT DATA – Scope of Work
NTT DATA | Confidential | Seatrium SAP Pegasus Migration
1
SAP System Migration
Export Pegasus from SAP RISE, provision new server in Seatrium Cloud, import SAP App + S/4HANA DB + GRC, validate display-only access
2
Archive Center
Support OpenText consultants in data separation and deletion, ensure local copy of attachments accessible from Seatrium Cloud
3
Access Management
Configure GRC for display-access request workflow, implement auto-termination of user IDs via AD/Workday batch jobs
4
Best Practices
Propose archival best practices for SAP data retention, ensure compliance with audit (5–7 yr) and SOT (10 yr) requirements

## Slide 7
Next Steps
NTT DATA | Confidential | Seatrium SAP Pegasus Migration
Immediate Actions
• Confirm scope and detailed requirements with Seatrium team
• Assess current Pegasus system size (DB, application, attachments)
• Define target architecture for Seatrium Cloud (server specs, OS, network)
• Align with OpenText consultants on archive separation plan
• Establish project timeline working back from Oct 2026 deadline
Key Milestones
• Aug 2026: Archive reduction 18TB → 16TB
• Oct 2026: SAP RISE contract end / cutover
• Post-migration: Validate display access & GRC
• Ongoing: User ID auto-termination monitoring
NTT DATA Team Actions
• Draft detailed migration plan & approach
• Prepare effort estimate & resource plan
• Schedule technical discovery workshop
• Identify archival best practice recommendations